# 1StudentID — Board Deck

MVP, Phased Roadmap & Segment Comparison

Product Team

July 2026

Table of Contents

1 — The Thesis	1

2 — What We Have Built	1

3 — The MVP: “Run My Institute Daily”	2

4 — Segment Comparison (the board’s decision)	2

5 — Phase 2: Monetization & Academic Depth	3

6 — Phase 3: Differentiation & Scale	3

7 — Full Timeline by Segment	3

8 — Indicative Cost	4

9 — Estimate Assumptions	5

10 — The Decision Before the Board	5

# 1 — The Thesis

We have already built the breadth. The job now is discipline, not more features.

- 24 modules exist and mostly work — excellent for the sales demo, dangerous as a first deployment.

- Ship a narrow, sticky daily-operations loop with a lead segment in 4–6 weeks, get one institute dependent on it, then let customer pull set the order of everything else.

- The board decision today is which segment to lead with — the module mix, effort, and timeline all shift by segment. This deck lays out all three so you can choose.

# 2 — What We Have Built

- Modular multi-tenant platform, one codebase, 24 entitlement-gated modules.

- Three proven verticals: schools, tuition / coaching institutes, sports & swim clubs.

- Four roles: student, parent (incl. co-parent), teacher / coach, admin (global + institute).

- Real differentiators (not generic SIS): Student Record Book, parent-rated Teacher Appraisal, Marketplace, per-institute white-label branding.

Current state: prototype UI is built. The work ahead is a production backend, multi-tenant data model, and hardening — not rebuilding screens.

# 3 — The MVP: “Run My Institute Daily”

The smallest complete loop that makes teachers, parents, and students show up every day.

Shared core (all segments): Core · Student Information · Courses · Attendance · Calendar · Teacher Workspace · Parent Portal · Messaging · Users & Roles · Light branding

Two deliberate additions:

- Student Record Book (SRB) — our stickiness engine; makes parents open the app daily.

- Multi-tenant data isolation — plumbing, not the franchise console. Skipping it now forces a rewrite later.

Explicitly out of MVP: Finance, LMS, Assignments, Grades, AI, Appraisal, Marketplace, CRM, Compliance, Migration.

# 4 — Segment Comparison (the board’s decision)

Each segment shares the core loop but weights different modules, which changes MVP size, effort, and time to first paying customer.

|  | Coaching / Tuition | Sports & Swim Clubs | Traditional Schools |
| --- | --- | --- | --- |
| Daily loop | Class + fee driven | Session + squad driven | Class + academic driven |
| Extra MVP modules | (lean core) | Sessions, Squad, Awards/Certs, Swim Reports | Grades, Assignments (expected day 1) |
| MVP effort | ~16–24 person-weeks | ~24–32 person-weeks | ~32–40 person-weeks |
| MVP timeline | 4–6 weeks | 6–8 weeks | 8–10 weeks |
| Time to first revenue | Fastest | Medium | Slowest |
| Deal size | Small–medium | Small | Largest |
| Market competition | High | Low (open field) | High |
| Recommendation | Best speed-to-revenue | Best differentiation | Best deal size, later |

Estimates assume a 4-person pod (3 engineers + 1 product/design), building a production backend on top of the existing prototype UI. Planning-grade, ±30%.

# 5 — Phase 2: Monetization & Academic Depth

Sequenced by revenue impact, not ease of build. ~5–7 weeks.

- Finance & Fees (build first) — for coaching/tuition buyers, fee collection is the real reason they buy. Turns “nice tool” into “must-have.”

- Grades & Gradebook + Assignments — academic core once attendance is trusted (already partly in Schools MVP).

- LMS — from admin tool to learning tool.

- Reports & BI — demanded the moment data flows.

- Teacher Training / CPD + Marketplace — adjacent revenue, network effects.

# 6 — Phase 3: Differentiation & Scale

~7–9 weeks.

- Franchise / multi-tenant management console — sell to chains.

- Teacher Appraisal (parent ratings) — novel marketing hook; ship after trust + data exist.

- AI Insights — high demo value; needs real history to avoid feeling gimmicky.

- Marketing & CRM — enrollment funnel for growth-minded institutes.

- Compliance & Audit + Migration — enterprise unlockers. Pull Migration forward if we lose deals to “we can’t move our data.”

- Full white-label branding — colours, vision/mission, custom domains.

# 7 — Full Timeline by Segment

Cumulative calendar time from project start, assuming one 4-person pod working sequentially through the phases.

| Milestone | Coaching / Tuition | Sports & Swim Clubs | Traditional Schools |
| --- | --- | --- | --- |
| MVP live | Week 4–6 | Week 6–8 | Week 8–10 |
| Phase 2 complete (Finance + academics) | Month 2.5–3 | Month 3–3.5 | Month 3.5–4 |
| Phase 3 complete (full platform) | Month 4.5–5 | Month 5–5.5 | Month 5.5–6.5 |

Add a second pod to compress Phase 2 and Phase 3 by roughly 30–40%, since those modules parallelize well once the foundation exists.

### Visual timeline (one pod, sequential)

Legend: ▓ MVP · ▒ Phase 2 · ░ Phase 3

| Segment | M1 | M2 | M3 | M4 | M5 | M6 | M7 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Coaching | ▓ | ▒ | ▒ | ░ | ░ |  |  |
| Clubs | ▓ | ▓ | ▒ | ▒ | ░ | ░ |  |
| Schools | ▓ | ▓ | ▓ | ▒ | ▒ | ░ | ░ |

# 8 — Indicative Cost

Cost is expressed as pod-months (rate-agnostic) so the board can apply its own blended team cost. One pod = 4 people (3 engineers + 1 product/design).

Cost = pod-months × your blended monthly pod cost.

| Segment | To MVP | To Phase 2 complete | To full platform |
| --- | --- | --- | --- |
| Coaching / Tuition | ~1–1.5 pod-months | ~2.5 pod-months | ~4.5 pod-months |
| Sports & Swim Clubs | ~1.5–2 pod-months | ~3 pod-months | ~5 pod-months |
| Traditional Schools | ~2–2.5 pod-months | ~3.5 pod-months | ~5.5–6 pod-months |

Illustrative only — replace the monthly rate with your actual blended, fully-loaded pod cost:

| Blended pod cost / month | MVP (Coaching) | Full platform (Coaching) |
| --- | --- | --- |
| Rate A — [replace] | 1.25 × Rate A | 4.5 × Rate A |
| Rate B — [replace] | 1.25 × Rate B | 4.5 × Rate B |

A second pod shortens the calendar by ~30–40% but does not materially change total pod-months (cost), since it buys speed, not efficiency.

# 9 — Estimate Assumptions

- Team: one 4-person pod — 3 engineers + 1 product/design. A second pod compresses Phases 2–3.

- Scope of “effort”: productionizing an existing prototype — real backend, multi-tenant data model, RBAC, data integrity, testing, and deployment. Screens largely exist.

- One-time foundation (inside MVP): authentication, tenant-scoped data model, RBAC, CI/CD, and infrastructure. Every later phase depends on it.

- Confidence: planning-grade, ±30%. Numbers tighten once segment and backend stack are fixed.

# 10 — The Decision Before the Board

Choose the lead segment. Everything else sequences from it.

- Fastest to revenue → Coaching / Tuition (MVP in 4–6 weeks, smallest lift).

- Strongest differentiation → Sports & Swim Clubs (open market, distinctive product).

- Largest deals, patient capital → Traditional Schools (biggest MVP, longest cycle).

Finance is confirmed as a Phase 2 fast-follow (built first in Phase 2), keeping the MVP lean regardless of segment.

Recommendation: lead with Coaching / Tuition for speed-to-revenue and cash generation, while keeping the Clubs demo warm as a differentiated second market — both reuse the same core with minimal added work.